## ชีต1
User Story | User Story / Acceptance Criteria | Description | Frontend (MH) | Backend (MH) | Total
Authentication
Email Registration | As a user, I want to sign up using my email so I can create an account. | - สมัครด้วยอีเมล | 2 | 2 | 4
Email Login | As a user, I want to log in with my email and password to access my dashboard. | - login ด้วย email/password - password required at least 8 letters | 2 | 2 | 4
Line Login | As a user, I want to log in with Line account. |  | 3 | 6 | 9
Google Login | As a user, I want to log in with Google account. |  | 3 | 6 | 9
Password Recovery | As a user, I want to receive a reset link via email if I forget my password. | - draft หน้าตา email ใน design (logo/header/footer) - หน้าสำหรับกรอก email ที่ต้องการส่งลิ้งค์สำหรับ reset password - ต้องเช็คว่า email มีในระบบหรือไม่ | 2 | 2 | 4
Password Recovery Screen | As a user, I want a screen to create a new password. | - กดลิ้งค์ใน email แล้วเข้าหน้านี้ - พอกรอกเสร็จให้เข้าหน้า dashboard ได้เลย | 2 | 1 | 3
Dual-Role System | As a user, I want to choose or switch between Entrepreneur and Influencer roles. | - email ซ้ำกันไม่ได้ ระหว่าง Entrepreneur / Influencer | 1 | 1 | 2
General Feature
Multi-Language Support | Support for TH/EN (Initial phase). | toggle มุมบนขวาของ ui | 2 | 0 | 2
Global Header | As a user, I want to see a main header on every page. |  | 3 | 0 | 3
Wallet Management | As a user, I want a dedicated pages to Deposit and Withdraw money. | - ฝากเงินเข้าระบบ (Kbank possible ถ้าธนาคารอื่นต้องขอเช็คอีกที) 1. qrcode 2. upload slip - ถอนเงินออกจากระบบ 1. เลขบัญชี required ในหน้า profile ของทั้งสองฝั่ง | 3 | 0 | 3
Deposit via QRcode | As an influencer, I want to deposit coins into my creator platform wallet by generating and scanning a QR code, so that I can quickly and securely top up my account. | - QR 15 นาที | 4 | 8 | 12
Deposit via slip upload | As an influencer, I want to deposit coins into my creator platform wallet by uploading a payment slip after transferring money. |  | 2 | 8 | 10
Coin Withdrawal | As an influencer, I want to withdraw coins from my account to my bank account so that I can receive my earnings from the platform. | - เลือกบัญชีที่ต้องการ - ขึ้น confirm | 3 | 8 | 11
Privacy Consent (Cookie) | As a user, I want to be notified about the use of cookies and have the option to accept or customize them |  | 3 | 2 | 5
Terms and Conditions Access | As a user, I want to easily access and read a clear, organized Terms and Conditions page. | - เก็บไว้หลังบ้านละยิง api เรียก | 3 | 2 | 5
Human Verification (CAPTCHA) | As a user, I want to see a CAPTCHA challenge on the login screen, So that we can prevent automated "brute-force" attacks and ensure only genuine human users are attempting to access accounts. |  | 4 | 3 | 7
Project Payment (Paypal) | As an Entrepreneur, I want to pay for an influencer's service using PayPal. So that I can fund the project securely using my preferred global payment method without re-entering my credit card details |  | 3 | 8 | 11
Earning Withdrawal (Paypal) | As an Influencer, I want to link my PayPal email address and withdraw my earned "Coins" to my PayPal account, So that I can receive my payment quickly in my local currency. |  | 3 | 8 | 11
Influencer Feature
Global Navigation | As an influencer, I want a header menu to switch between the Marketplace, My Applications, Direct Invites, Current Balance, Pending Submissions, My Profile so I can manage my workflow. | Marketplace = Main Screen (Left Header) My Applications = Application Direct Invites = Direct Pending Submission = Submission Current Balance = Dropdown (Right Header) My Profile = Dropdown (Right Header) | 3 | 0 | 3
View Job Overview | As an influencer, I want to see a grid of job cards containing the Budget, Category, Brand Name, Location, and Platform Type (e.g., TikTok/IG) to quickly evaluate opportunities. | - หน้า Marketplace - infinite scroll - click เข้าไปดูรายละเอียดได้ | 3 | 2 | 5
Live Wallet Balance | As an influencer, I want to see my current coins(e.g., 1500.00) in the header so I can track my earnings. | - อัพเดตทันที | 2 | 2 | 4
Search and Filtering | As an influencer, I want to search and filter the marketplace by keywords, category, budget, platform, and location, so that I can quickly find and apply for the most relevant and high-paying campaigns that match my specific content niche and social media channels. | - search ด้วย job name/ entreprenuer name - filter ด้วย category, budget range, location, platform | 2 | 1 | 3
View Entrepreneur Overview | As an influencer, I want to see a grid of entrepreneur cards containing their detail, products, and review | - เข้าจากหน้าค้นหา/รายละเอียดของงาน | 1 | 1 | 1
Invite Notifications | As an influencer, I want to see a red dot or number badge on the "Direct Invites" tab when a brand sends me a new offer. | - noti บน tab Direct Invites - ขึ้นเตือนทันที | 2 | 2 | 4
Balance Notifications | As an influencer, I want to see a red dot or number badge on the "Current Balance" when I receive coins. | - หน้า Current Balance - noti เวลา coin เข้า | 1 | 1 | 2
Coin History | As an influencer, I want to access a detailed chronological log of all my coin transactions, So that I can track my earnings. |  | 3 | 2 | 5
Track My Applications | As an influencer, I want to see a list of jobs I applied for, along with the status: Pending Review, Rejected, or Accepted | - หน้า My Applications - click เข้าไปดูรายละเอียดได้ | 3 | 2 | 5
Withdraw Application | As an influencer, I want the ability to withdraw my request if I am no longer available for that specific job. | - ยกเลิกได้ก่อน status Accepted | 1 | 1 | 2
Track Direct Invites | As an influencer, I want to see a list of direct invitations from brands, including the proposed budget and brief. | - หน้า Direct Invites - filter ตาม brand, ประเทศ, ราคา | 3 | 3 | 6
Accept / Decline Invites | As an influencer, I want two clear buttons: "Accept" (moves the job to 'Pending Submissions') and "Decline" (notifies the entrepreneur and removes it from the list). | - มี Confirm modal | 2 | 3 | 5
Job Info | As an influencer, I want to click into a job to view the full campaign brief—including budget, media type, duration, and content requirements—so that I can understand the expectations. |  | 1 | 2 | 3
Edit Profile | As an Influencer, I want to update my professional details, social media stats, and niche categories. | - ชื่อ-สกุล - ชื่อในวงการ - อายุ - รูป - Platform ที่มี - ประเภทของ content - Review - ภาษา - บัญชี - รูปอืิ่นๆ | 2 | 3 | 5
Submission Notifications | As an influencer, I want to see a red dot or number badge on the "Pending Submissions" when submitted job has problem(s) |  | 1 | 1 | 2
Track Pending Submissions | As an influencer, I want a dedicated page to view all my ongoing jobs, see their deadlines, and submit my work links, so that I can complete my assignments on time and officially close the job for payment. | - หน้า Pending Submissions - ช่องทางติดต่อฝั่ง business - ขยับ deadline? | 3 | 2 | 5
Submit Multiple Links | As an influencer, I want the submission form to automatically generate link fields based on the platforms required for that job, so that I can submit multiple specific work links required to complete the campaign requirements. | - มีหลายฟิลด์ให้กรอก เช่น tiktok/youtube/facebook | 2 | 2 | 4
Handle Rejected Work | As an influencer, I want to see rejected work with a button to "Submit again" and "Report admin" | - list of rejected work - สามารถเข้าไปดูรายละเอียดได้ - เมื่อกด report จะให้ใส่รายละเอียดก่อนส่ง | 2 | 2 | 4
Bill PDF | As an admin, I can print bill so that I can provide customers with a physical copy of their transactions. |  | 2 | 4 | 6
Entrepreneur Feature
Global Navigation | As an entrepreneur, I want a header menu to switch between Influencer Discovery, My Job Postings, Incoming Applications, Review Submissions, Current Balance, My Profile so I can manage my hiring workflow. | Influencer Discovery = Main screen (Left header) My Job Posting = Application Incoming Application = Direct Review Submission = Submission Current Balance = Dropdown (Right header) My Profile = Dropdown (Right header) | 3 | 0 | 3
Live Wallet Balance | As an entrepreneur, I want to see my current coins in the header so I know my available budget for hiring and paying influencers. | - อัพเดตทันที | 1 | 0 | 1
Application Notifications | As an entrepreneur, I want to see a red dot or number badge on the "Incoming Applications" tab when an influencer applies to my job. | - ขึ้นเตือนทันที | 1 | 1 | 2
Submission Notifications | As an entrepreneur, I want to see a red dot or number badge on the "Review Submissions" tab when an influencer submits their final work. | - ขึ้นเตือนทันที | 1 | 1 | 2
Balance Notifications | As an entrepreneur, I want to see a red dot or number badge on the "Current Balance" when I receive coins. | - หน้า Current Balance - noti เวลา coin เข้า | 1 | 1 | 2
Coin History | As an entrepreneur, I want to access a detailed chronological log of all my coin transactions, So that I can track my earnings. |  | 3 | 1 | 4
View Influencer Overview | As an entrepreneur, I want to see a grid of influencer cards containing their niche, follower count, platform type, and average rating to quickly evaluate potential hires. | หน้า Influencer Discovery | 3 | 2 | 5
Search and Filtering | As an entrepreneur, I want to search and filter the influencer directory by keywords, category, follower range, platform, rating, and location, so I can find the perfect match for my campaign. | - search: influencer name - filter: platform, language, category | 2 | 2 | 4
Influencer Info (Profile) | As an entrepreneur, I want to click into an influencer's profile to view their detailed stats, portfolio links, and past reviews so I can make an informed hiring decision. |  | 2 | 1 | 3
Create/Edit Job Postings | As an entrepreneur, I want a form to create and publish new job briefs—including budget, media type, duration, and requirements—so influencers can find and apply to them. | หน้า My Job Postings - แสดง list ของงานที่สร้าง - เลือกได้ว่า public / private | 2 | 3 | 5
Track Incoming Applications | As an entrepreneur, I want to see a list of influencers who have applied to my open jobs, including a link to their profile. | หน้า Incoming Applications - แสดง list ของงานที่มี influencer มาสมัคร - แสดง influencer ที่มาสมัครด้วย ตามงาน - กดเข้าไปดูข้อมูล influencer ได้ | 3 | 1 | 4
Accept / Reject Applications | As an entrepreneur, I want two clear buttons on incoming applications: "Accept" (hires the influencer and moves the job to Review Submissions) and "Reject" (declines their application). | มี confirm modal | 2 | 2 | 4
Send Direct Invites | As an entrepreneur, I want a "Hire/Offer Job" button on an influencer's profile so I can bypass the public marketplace and send them a private offer. | - เลือก influencer จากหน้า search - มีปุ่ม hire พอกดแล้วขึ้นให้เลือกงานที่เป็น private | 3 | 2 | 5
Track Sent Invites | As an entrepreneur, I want to track the status of direct invitations I've sent to influencers (Pending, Accepted, or Declined). | ดูจากใน incoming application | 2 | 1 | 3
Edit Brand Profile | As an entrepreneur, I want to update my company details, logo, and brand description so influencers trust my job postings. | หน้า My Profile | 2 | 1 | 3
Review Submitted Links | As an entrepreneur, I want a dedicated page to view the multiple specific work links submitted by influencers for completed campaigns. | หน้า Review Submissions - กดเข้าไปดูรายละเอียดงานที่ส่งได้ - มี status: submitted, pending review, pending re-submit | 2 | 3 | 5
Approve/Reject/Report | As an entrepreneur, I want to verify the submitted work and click "Accept & Pay" to release coins to the influencer, reject the submitted work and click "Reject" to allow influencer to fix, report issue of this collaboration with admin and click "Report Admin" | - เมื่อกด reject จะต้องใส่รายละเอียดเพิ่มเพื่อส่ง | 2 | 6 | 8
Rate & Review | As an entrepreneur, I want to leave a star rating (1-5) and written review for the influencer within 30 days of completing the job to help maintain platform quality. | - ตั้งไว้ให้เซตได้ภายใน 30 วัน | 2 | 2 | 4
Bill PDF | As an admin, I can print bill so that I can provide customers with a physical copy of their transactions. |  | 2 | 3 | 5
Administration
Global Navigation | As an entrepreneur, I want a header menu to switch between User List, Report Issue so I can manage my hiring workflow. |  | 3 | 0 | 3
User Directory | As an admin, I want to see a searchable list of all registered users (Influencers and Entrepreneurs) with their current status, so I can monitor platform activity. | หน้า User List - search: name - filter: role, language, coin, ban - กดเข้าไปดูได้ | 3 | 3 | 6
Ban/Suspend User | As an admin, I want the ability to change a user's status to "Banned" so that I can immediately block bad actors from logging in or interacting with others. | มีปุ่มแบน | 1 | 2 | 3
Unban/Restore User | As an admin, I want the ability to restore a previously banned account, so I can fix mistaken bans or lift temporary suspensions. | มีปุ่มยกเลิกแบน | 1 | 2 | 3
User Details View | As an admin, I want to click on a user to see their transaction history, active jobs, and received reviews , so I have full context before making a moderation decision. | รวมในหน้า profile เป็นเมนูย่อย | 3 | 2 | 5
Dispute Queue | As an admin, I want to see a queue of all jobs marked as "Report Issue," so I can review cases where the Entrepreneur and Influencer disagree on the submitted work. | หน้า Report Issue - กดเข้าไปดูรายละเอียดได้ | 2 | 1 | 3
Review Evidence | As an admin, I want to see the original job brief, the submitted links, and any messages/reports from both parties to make an informed decision on a dispute. | แสดงในรายะเอียดที่กดจากหน้า Report Issue | 1 | 1 | 2
Manual Fund Override | As an admin, I want the authority to manually force a transaction to either Refund the Entrepreneur or Release Coins to the Influencer, so I can officially close a disputed job. | - เพิ่ม 2 ปุ่มในการบังคับ - กรอกตัวเลขได้ | 3 | 4 | 7
Change Request v1
Other
UX/UI Design |  |  | 14 | 0 | 14
Deployment Setup |  |  | 0 | 8 | 8
System Design |  |  | 0 | 8 | 8
Project Setup |  |  | 6 | 6 | 12
|  | Total Manhour | 163 | 173 | 336
|  | Total Cost | 81500 | 86500 | 168000
Todo
Accountant Program Integration | As an admin, I can integrate the system with an accounting program so that financial data is automatically recorded and managed.